## Slide 1: Fundamental of Software Engineering
Chapter 6
Software Project Management
Departemnt of Software Enginnering
June 14, 2023

## Slide 2: Software Project Management
Concerned with activities involved in ensuring that software is delivered on time and on schedule and in accordance with the requirements of the organisations developing and procuring the software.
Project management is needed because software development is always subject to budget and schedule constraints that are set by the organisation developing the software.

## Slide 3: Cont..

## Slide 4: Project Management Skills
Leadership
Communications
Problem Solving
Negotiating
Influencing the Organization
Mentoring
Process and technical expertise

## Slide 5: The Four P’s in Management
People — the most important element of a successful project
Product — the software to be built
Process — the set of framework activities and software engineering tasks to get the job done
Project — all work required to make the product a reality

## Slide 6: Stakeholders in project management
Senior managers who define the business issues that often have significant influence on the project.
Project (technical) managers who must plan, motivate, organize, and control the practitioners who do software work.
Practitioners who deliver the technical skills that are necessary to engineer a product or application.
Customers who specify the requirements for the software to be engineered and other stakeholders who have a peripheral interest in the outcome.
End-users who interact with the software once it is released for production use.

## Slide 7: Software Teams
How to lead?
How to organize?
How to motivate?
How to collaborate?
How to create good ideas?

## Slide 8: Role of Team Leader
The MOI Model
  Motivation. The ability to encourage (by “push or pull”) technical people to produce to their best ability.
  Organization. The ability to mold existing processes (or invent new ones) that will enable the initial concept to be translated into a final product.
  Ideas or innovation. The ability to encourage people to create and feel creative even when they must work within bounds established for a particular software product or application.

## Slide 9: Software Teams
the difficulty of the problem to be solved
the size of the resultant program(s) in lines of code or function points
the time that the team will stay together (team lifetime)
the degree to which the problem can be modularized
the required quality and reliability of the system to be built
the rigidity of the delivery date
the degree of sociability (communication) required for the project
The following factors must be considered when selecting a software project team structure ...

## Slide 10: Organizational Paradigms
closed paradigm—structures a team along a traditional hierarchy of authority
random paradigm—structures a team loosely and depends on individual initiative of the team members
open paradigm—attempts to structure a team in a manner that achieves some of the controls associated with the closed paradigm but also much of the innovation that occurs when using the random paradigm
synchronous paradigm—relies on the natural compartmentalization of a problem and organizes team members to work on pieces of the problem with little active communication among themselves
suggested by Constantine [Con93]

## Slide 11: Software Management Distinctions
The product is intangible.
The product is uniquely flexible.
Software engineering is not recognized as an engineering discipline with the same status as mechanical, electrical engineering, etc.

## Slide 12: Cont.
We don’t have much experience.
  Software engineering is a new discipline, and so we simply don’t have much understanding of how to engineer large scale software projects.
Large software projects are often “bespoke”.
  Most large software systems are one-off, with experience gained in one project being of little help in another.
The technology changes very quickly.
  Most large software projects employ new technology; for many projects,

## Slide 13: Activities in software project management:
Project Planning
Project Scheduling
Risk Management
Managing people

## Slide 14: 1. Project Planning
The biggest single problem that afflicts software developing is that of underestimating resources required for a project.
Developing a realistic project plan is essential to gain an understanding of the resources required, and how these should be applied.

## Slide 15: 1.1 Types of plan:
Software development plan.
  The central plan, which describes how the system will be developed.
Quality assurance plan.
  Specifies the quality procedures & standards to be used.
Validation plan.
  Defines how a client will validate the system that has been developed.

## Slide 16: Cont.
Configuration management plan.
  Defines how the system will be configured and installed.
Maintenance plan.
  Defines how the system will be maintained.
Staff development plan.
  Describes how the skills of the participants will be developed.

## Slide 17: Project planning process
Establish the project constraints
Make initial assessments of the project parameters
Define project milestones and deliverables
while project has not been completed or cancelled loop
Draw up project schedule
Initiate activities according to schedule
Wait ( for a while )
Review project progress
Revise estimates of project parameters
Update the project schedule
Re-negotiate project constraints and deliverables
if ( problems arise ) then
Initiate technical review and possible revision
end if
end loop

## Slide 18: 1.2 The Software Development Plan
This is usually what is meant by a project plan.
Specifies the order of work to be carried out, resources, responsibilities, and so on.
Varies from small and relatively informal to large and very formal.
Developing a project plan is as important as properly designing code:
  On the basis of a project plan, contracts will be signed and careers made or broken. . .
Important not to:
      overestimate your team’s ability;
      simply tell clients what they want to hear;
      be pressured by developers (“we can do that in an afternoon!”)

## Slide 19: 1.2.1 Structure of Development Plan
1. Introduction
  brief intro to project — references to requirements spec
2. Project organization
  intro to organizations, people, and their roles
3. Risk Analysis
  what are the key risks to the project?

## Slide 20: Cont.
4. Hardware and software resources
  what h/ware and s/ware resources will be required for the project and when?
5. Work breakdown
  the project divided into activities , milestones, deliverables; dependencies between tasks etc
6. Project schedule
  actual time required — allocation of dates
7. Reporting and progress measurement : mechanisms to
monitor progress.

## Slide 21: 1.2.2 Work Breakdown
There are many ways of breaking down the activities in a project, but the most usual is into:
  work packages;
  tasks;
  deliverables;
  milestones.

## Slide 22: Cont.
A workpackage is a large, logically distinct section of work:
typically at least 12 months duration;
may include multiple concurrent activities;
independent of other activities;
but may depend on, or feed into other activities;
typically allocated to a single team.

## Slide 23: Cont.
task is typically a much smaller piece of work:A part of a workpackage.
typically 3–6 person months effort;
may be dependent on other concurrent activities;
typically allocated to a single person.

## Slide 24: Cont.
A deliverable is an output of the project that can meaningfully be assessed.
-is a measurable and tangible outcome of the project
Examples: – a report (e.g., requirements spec);
code (e.g., alpha tested product).
Deliverables are indicators (but only indicators) of progress.
A milestone is a point at which progress on the project may be assessed.
-are checkpoints throughout the life of the project
Typically a major turning point in the project.
EXAMPLES: – delivery of requirements spec;
delivery of alpha tested code.

## Slide 25: 2.Project Scheduling
Split project into tasks and estimate time and resources required to complete each task.
Organize tasks concurrently to make optimal use of workforce.
Minimize task dependencies to avoid delays caused by one task waiting for another to complete.
Dependent on project managers intuition and experience.

## Slide 26: 2.1 The project scheduling process

## Slide 27: 2.2 Scheduling problems
Estimating the difficulty of problems and hence the cost of developing a solution is hard.
Productivity is not proportional to the number of people working on a task.
Adding people to a late project makes it later because of communication overheads.
The unexpected always happens. Always allow contingency in planning.

## Slide 28: 2.3 Bar charts and activity networks
Graphical notations used to illustrate the project schedule.
Show project breakdown into tasks. Tasks should not be too small. They should take about a week or two.
Activity charts show task dependencies and the critical path.
Bar charts show schedule against calendar time.

## Slide 29: Task durations and dependencies

## Slide 30: Activity network

## Slide 31: Activity timeline

## Slide 32: Staff allocation

## Slide 33: 3. Risk Management
Risk management is concerned with identifying risks and drawing up plans to minimise their effect on a project.
A risk is a probability that some adverse circumstance will occur
  Project risks affect schedule or resources;
  Product risks affect the quality or performance of the software being developed;
  Business risks affect the organisation developing or procuring the software.

## Slide 34: 3.1 Software risks

## Slide 35: 3.2 The risk management process
Risk identification
  Identify project, product and business risks;
Risk analysis
  Assess the likelihood and consequences of these risks;
Risk planning
  Draw up plans to avoid or minimise the effects of the risk;
Risk monitoring
  Monitor the risks throughout the project;

## Slide 36: 3.3 The risk management process

## Slide 37: 3.3.1 Risk identification
Technology risks.
People risks.
Organisational risks.
Requirements risks.
Estimation risks.

## Slide 38: Risks and Risk types

## Slide 39: 3.3.2 Risk analysis
Assess probability and seriousness of each risk.
Probability may be very low, low, moderate, high or very high.
Risk effects might be catastrophic, serious, tolerable or insignificant.

## Slide 40: Risk analysis (i)

## Slide 41: Risk analysis (ii)

## Slide 42: 3.3.3 Risk planning
Consider each risk and develop a strategy to manage that risk.
Avoidance strategies
  The probability that the risk will arise is reduced;
Minimisation strategies
  The impact of the risk on the project or product will be reduced;
Contingency plans
  If the risk arises, contingency plans are plans to deal with that risk;

## Slide 43: 3.3.4 Risk management strategies (i)

## Slide 44: Risk management strategies (ii)

## Slide 45: 3.3.5 Risk monitoring
Assess each identified risks regularly to decide whether or not it is becoming less or more probable.
Also assess whether the effects of the risk have changed.
Each key risk should be discussed at management progress meetings.

## Slide 46: 3.3.6 Risk Indicators

## Slide 47: 4. Project Size Estimation Metrics
Size is one of the most important attributes of a software product
CODE-BASED SIZING METRICS
Code-based sizing metrics measure the size or complexity of software using the programmed source code. Because a significant amount of effort is devoted to programming, it is believed that an appropriate measure correctly quantifying the code can be a perceivable indicator of software cost.

## Slide 48: Cont..
source lines of code (SLOC) among others have been proposed and used as code-based sizing metrics.
SLOC is the most popular. It is used as a primary input by most major cost estimation models, such as SLIM, SEER-SEM, PRICE-S,COCOMO, and Knowledge Plan

## Slide 49: Cont.…
The Constructive Cost Model (COCOMO) is a formula-based method for estimating the total cost of developing software .
The fundamental input to COCOMO is the estimated number of lines of source code.

## Slide 50: Cont.
Function Point Analysis(FPA) estimates the cost of a project from the estimates of the delivered functionality
FPA can therefore be applied at the end of the software requirements definition phase to make cost estimates.

## Slide 51: Key points
Good project management is essential for project success.
The intangible nature of software causes problems for management.
Managers have diverse roles but their most significant activities are planning, estimating and scheduling.
Planning and estimating are iterative processes which continue throughout the course of a project.

## Slide 52: Key points
A project milestone is a predictable state where a formal report of progress is presented to management.
Project scheduling involves preparing various graphical representations showing project activities, their durations and staffing.
Risk management is concerned with identifying risks which may affect the project and planning to ensure that these risks do not develop into major threats.

## Slide 53
Thank You!
Q?